## Delivery Plan
Version | Delivery to NDL
v3.1 | 01.06.11
Jun20 HF | 20.06.11
Jul20 HF | 20.07.11
Aug10 HF | 10.08.11

## Musts
No. | Issue (Roadblocks => Red No fullfillment stage => Yellow) | Date last status change | Road block? | Priority 1 = highest 100 = lowest | SI number | Ex Libris' Comments | To be delivered with | Stage of fulfillment | Current Status | Next Steps | Actor | Description/Notes | Topic | Must have b4 go live? | Origin
31 | 11.2 External authentication methods and extensions (OpenID, custom authentication hooks, e.g. library card number + PIN code from a local library, Finnish VETUMA identification and payment system) | 2011-05-23 | Yes |  |  | OvP needs to be tested completely. Therefore Alessandro set up authentication for Univ. of Jväskylä - completed on 23 May |  | Implementation | PDS set up against Voyager to start testing FE look &feel for OVP | Test OvP for Voyager | NDL | Authentication for Voyager is set up | Authentication | Yes | FTR Vaski
21 | 6.2 The end-user must be able to check and pay fees such as hold fees, overdue fees and other service fees (online payment etc.) | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL | payment of fines is not a must, checking fines is. | OVP API / FE | Yes | FTR Vaski
20 | 6.1 The end-user must be able to check and renew loans | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | FTR Vaski
22 | 6.3.1 The end-user must be able to reserve materials | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | FTR Vaski
24 | 6.3.7 The end-user must be able to check the availability of an item (for example holdings information) | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | FTR Vaski
41 | Displaying of patron's contact information (name, address, email, phone number) | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | List from Vaski
42 | Displaying of patron's active notification methods for request arrival notifications, overdue letters and due date notifications (email, SMS, letter) | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | List from Vaski
43 | Displaying of patron's loans (name of work, due date, number of renewals) | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | List from Vaski
44 | Renewal of loans | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | List from Vaski
45 | Requests, including requesting of on-shelf material | 2011-05-05 | affected |  |  |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL |  | OVP API / FE | Yes | List from Vaski
10 | 16384-241641:HIGH: (L3 Problem Report) [358FIN] : Security issue: Back Office / | 2011-05-05 |  |  | 16384-241641 | Fixed on May-1, will be delivered as part of v3.1 | 3.1 | Delivery |  | Deliver fix | EXL |  | Security | Yes | SI list
12 | 16384-237819:: (L3 Problem Report) [358FIN] : Primo creates excessively long RSS URLs | 2011-05-05 |  |  | 16384-237819 | Fixed on Mar-29, will be delivered as part of v3.1 | 3.1 | Delivery |  | Deliver fix | EXL | F&TR 3.14 | FE links | Yes | SI list
13 | 16384-237973:: (L3 Problem Report) [358FIN] : Match of ISBN-10 to ISBN-13: (Pr | 2011-05-05 |  |  | 16384-237973 | Fixed. Will be delivered as part of v3.1 | 3.1 | Delivery |  | Deliver fix | EXL |  | FE data display & behaviour | Yes | SI list
14 | 162096:: (L3 Problem Report) [49EXL] : How to customize character normalization (2-Unicodes-Characters to 1- Unicode-Characters) | 2011-05-05 |  |  | 162096 | Fixed on Apr-26, will be delivered as part of v3.1 Still missing the 'Display' part. In the meeting we has on May-3 we suggested NDL to handle the display using the Enrichment plug-in. Ere will look into it. | 3.1 | Delivery |  | Deliver fix | EXL | F&TR 3.16 + 15.2 | FE data display & behaviour | Yes | SI list
7 | 16384-247302:: (L3 Problem Report) [358FIN] : Primo should not suspect unsupported characters if different error causes search to fail | 2011-06-01 |  |  | 16384-247302 | Will be fixed as part of HF that will be provided 20 June. | Jun20HF | Development | preparing HF for after 3.1 |  | EXL |  | FE error messages | Yes | SI list
9 | 16384-242189:HIGH: (L3 Problem Report) [358FIN] : Security issue: Any user can change the notes of other users fiolders in the e-shelf | 2011-06-01 |  |  | 16384-242189 | Will be fixed as part of HF that will be provided 20 June. | Jun20HF | Development | preparing HF for after 3.1 |  | EXL | F&TR 5.10 | Security | Yes | SI list
15 | 162125:HIGH: (L3 Problem Report) [358FIN] : Component parts: (Primo) Product M | 2011-06-01 |  |  | 162125 | Ere presented his solution at HQ and explained which issues will remain. Discussed in Jerusalem and in further analysis. | customer code | Verification | a Javascript solution was created by NDL; confirmation from Vaski needed; large scale performance untested. | currently tested and optimized by NDL | NDL | see Aalborg; | FE data display & behaviour | Yes | SI list
4 | 16384-255076:: (L3 Problem Report) [358FIN] : Security Issue: Emailing records | 2011-05-11 |  |  | 16384-255076 | Fixed on May-5, will be delivered as part of v3.1 | 3.1 | Delivery |  | Deliver fix | EXL |  | Security | Yes | SI list
5 | 16384-254310:: (L3 Problem Report) [358FIN] : Primo does not sanitize email sub | 2011-06-01 |  |  | 16384-254310 | Will be fixed as part of HF that will be provided 20 June. | Jun20HF | Development | preparing HF for after 3.1 |  | EXL |  | Security | Yes | SI list
8 | 16384-244695:: (L3 Problem Report) [358FIN] : Punctuation in brief results - no delimiters can be defined between the fields used on the same line in the Brief Results (in the full results you can) | 2011-06-01 |  |  | 16384-244695 | Will be fixed as part of HF that will be provided 10 August. | Aug10HF | Development |  | Discuss at HQ | EXL |  | FE data display & behaviour | Yes | SI list
11 | 16384-240952:: (L3 Problem Report) [358FIN] : Unable to terminate harvesting pipe | 2011-06-01 |  |  | 16384-240952 | Will be fixed as part of HF that will be provided 20 July. | Jul20HF | Development | it happens because of threads that are not finished - will be fixed. | Analysing | EXL |  | BO publishing | Yes | SI list
16 | 1.8 The end user must be able to use persistent links to references (the link can be bookmarked, saved or sent by e.g. e-mail). | 2011-06-01 |  |  | 164751 | Will be fixed as part of HF that will be provided 20 June. | Jun20HF | Development | At least scandinavian characters in a search term are lost when a bookmarked search is repeated and no existing Primo session is active (SSO process encoding issue?) | Analysing | ExL |  | FE links | Yes | FTR Vaski
19 | 4.2.1 It should be possible prioritise organisation's own material in its view of the public interface. We value customisability of the relevance ranking system. | 2011-05-04 |  |  |  | The 'Boosting by Institution' will be provided as part of v3.1. In the meeting we had on May-3 NDL were happy with the 'Boosting by Institution' solution but they would like to have in addition 'Boosting by Scope' - this is not a MUST for september. Tami will prepare this issue for the visit. We will discuss it with NDL next week. | 3.1 | Delivery | Institutional Boost discussed in call 4.5.2011; solution described there was considered adequate for current purposes by NDL | Deliver fix | EXL |  | FE data display & behaviour | Yes | FTR Vaski
25 | 9.2.1 Possibility to limit user session statistics reports based on user-groups, organisation and date interval. | 2011-06-01 |  |  | 164749 | Will be fixed as part of HF that will be provided 20 July. | Jul20HF | Development |  | Analysing | ExL |  | Statistics | Yes | FTR Vaski
26 | 9.8 The system should record statistics separately per access method (web interface, API etc.) and provide the possibility to distinguish between the methods in statistics reports. esp. number of real searches | 2011-06-01 |  |  | 164750 | Will be fixed as part of HF that will be provided 20 July. | Jul20HF | Development | E.g. the component parts implementation that uses X-Services must not skew the web interface usage statistics | Analysing | ExL |  | Statistics | Yes | FTR Vaski
28 | 10.19 No limitation to session duration as long as the user has the service open in the browser (e.g. provide a possibility to use a JavaScript keep-alive callback to keep the session alive) | 2011-06-01 |  |  |  | NDL explained on 11 May that they do not want the session to keep alive but as long as the user's browser is open they want the browser to ping to the server and once the user close the browser, the session will end. | customer code | Discussing solutions | NDL considers use of local javascript? But needs to know: What url to use to keep the session alive (ping)? | Discuss at HQ | EXL / NDL |  | FE session behaviour | Yes | FTR Vaski
29 | 10.23 Item availability status via batch load for facets and display of real time updated status per user affiliation (institution, IP address) | 2011-05-11 | Yes |  |  | This issue relate to RTA. NDL agreed that EXL will develop the RTA for them. Frank Bieber contacted Bjarne. We are waiting for for a new version of Axiell webservices. The timetable for this will be clear within the next days. Actually I also have to make sure that Axiell actually allows to give the specifications to another vendor and on which level. The access is restricted to certain IP:s. |  | Pending - Implementation | Pending Implementation | RTA needs to be configured first. Frank Bieber should set it up and give seminar/workshop and documentation how he's done it. We are waiting for a new version of Axiell web services - to be delivered w/c 16 May - Bjarne to follow up w/c 23 May. | NDL | Basically means: Correct display of calculated RTA in full display according to user/institution/ip | RTA | Yes | FTR Vaski
30 | 10.24.1 Possibility to display item availability by items' institutions and location on the search results list without having to move to a different per-record display | 2011-05-11 | Yes |  |  | Same as #29 |  | Pending - Implementation | Pending Implementation | RTA needs to be configured first. Frank Bieber should set it up and give seminar/workshop and documentation how he's done it. We are waiting for a new version of Axiell web services - to be delivered w/c 16 May - Bjarne to follow up w/c 23 May. | NDL | Basically means: Correct display of calculated RTA in brief results display according to user/institution/ip | FE data display & behaviour | Yes | FTR Vaski
34 | 12.10 Relevance ranking | 2011-05-05 | affected |  |  |  |  | Testing | Pending - Needs to be tested with real data | waiting for harvesting issue to be solved and thus data to be harvested (see issue 6) | NDL |  |  | Yes | FTR Vaski
36 | 15.2 Support Unicode (UTF-8) in all functions and provide conversions to/from other character sets e.g. ISO-8859-15 | 2011-05-11 | [5 empty] | Analysing |  | Ere to split into individual issues per function | NDL |  | FE data display & behaviour | Yes | FTR Vaski
38 | 18.3 24 / 7 continuous availability Change IP Address requires FE restart Change API URL requires FE restart | 2011-06-01 |  |  | 164916 | Will be fixed as part of HF that will be provided 20 July. | Jul20HF | Development |  | Discuss at HQ | ExL |  |  | Yes | FTR Vaski
46 | Performance of services | 2011-05-05 | [5 empty] | Pending - Testing |  |  | NDL | Needs to be adequate |  | Yes | List from Vaski
48 | Trouble with stemming (and disabling it) | 2011-06-01 |  |  | 16384-259281 | Will be fixed as part of HF that will be provided 20 July. | Jul20HF | Development |  | Deliver fix | ExL | Stemming works incorrectly with Finnish terms - can it be deactivated (if so how)? | SE behaviour
49 | Did you mean problem with dashes in search terms | 2011-06-01 |  |  | 16384-260149 | Will be fixed as part of HF that will be provided 10 August. | Aug10HF | Development |  | Deliver fix | ExL |  | SE behaviour
50 | Problems with dashes in search terms | 2011-06-01 |  |  | 16384-260146 | Will be fixed as part of HF that will be provided 10 August. | Aug10HF | Development |  | Deliver fix | ExL |  | SE behaviour
51 | 16384-263534 RTA shows wrong information when moving back in Firefox | 2011-05-23 |  |  | 16384-263534 | NEW - needs prioritisation - ExL is checking whether it can be included in Aug10 HF |  | Analysing |  | Analysing | ExL |  | RTA | yes

## Maybes
No. | Issue | Date last status change | Road block? | SI number | To be delivered with | Stage of fulfillment | Current Status | Next Steps | Actor | Description/Notes | Topic | Must have b4 go live? | Origin
23 | 6.3.4 The end-user must be able to do interlibrary loans and material requests |  | affected |  |  | Pending - Testing | Discuss setup of PDS against Voyager to start testing | Check with Vaski if necessary | NDL |  | OVP API / FE | Maybe | FTR Vaski
1 | 16384-255080:: (L3 Problem Report) [358FIN] : Wrong links in emails sent from P |  |  | 16384-255080 |  | Development |  | get current Dev status | EXL |  | FE links | Maybe | SI list
2 | 16384-242192:: (L3 Problem Report) [358FIN] : eShelf and record folder notes do |  |  | 16384-242192 |  | Development |  | get current Dev status | EXL |  | FE E-Shelf | Maybe | SI list
3 | 16384-239903:: (L3 Problem Report) [358FIN] : Stopping a pipe pending terminati |  |  | 16384-239903 |  | Pending - Analysis | ExL w4i when another pipe is going to be started | get current Dev status | EXL |  | BO publishing | Maybe | SI list
27 | 10.13 Persistent URLs to all functions | [9 empty] | API | Maybe | FTR Vaski
33 | 12.9 Facets customisable per view (which ones are displayed, order of display) | 2011-05-05 |  |  |  | Implementation |  |  |  |  | FE data display & behaviour | Maybe | FTR Vaski
39 | Lightweight authentication (e.g. OpenID) | [5 empty] | Priority needs to be checked with Turku |  |  |  | Authentication | Maybe | List from Vaski

## Duplicates
No. | Issue | Date last status change | Road block? | SI number | To be delivered with | Stage of fulfillment | Current Status | Next Steps | Actor | Description/Notes | Topic | Must have b4 go live? | Origin
32 | 12.1 Harvest records into the indexes using OAI-PMH protocol | 2011-05-05 | Yes |  | Hotfix, 5.5.2011 | Verification | resumptionToken problem, fix pending testing |  | NDL | Duplicate with 6 | BO publishing | Duplicate | FTR Vaski
18 | 3.14 The end-user must be able to create alerts that send information on new references matching the search criteria by e-mail or RSS feed | [5 empty] | RSS Feed URLs too long |  |  | Duplicate with 1 and 12 | FE links | Duplicate | FTR Vaski
40 | Displaying of fees (amount and reason) |  | affected |  |  | Pending-Testing | Pending | Discuss setup of PDS against Voyager to start testing | NDL | Duplicate with 21 | OVP API / FE | Yes | List from Vaski
48 | Statistics report on the number of sessions |  |  |  |  | Duplicate! |  |  |  | Duplicate to 25 | Statistics | Yes | List from Vaski
35 | 13.6 Retrieve and modify patron information, loans, holds and payments using SOAP or REST |  | affected |  |  | Duplicate! | Pending | Verfiy Duplicate status; Discuss setup of PDS against Voyager to start testing | NDL | Duplicate with 20 / 22/ 41 | OVP API / FE | Yes | FTR Vaski
37 | 15.3 Holds, loan renewals and item availability from library systems using APIs such as the ones specified by DLF's ILS-DI task group |  | affected |  |  | Duplicate! | Pending | Verfiy Duplicate status; Discuss setup of PDS against Voyager to start testing | NDL | Duplicate with 20 / 22/ 24 | OVP API / FE | Yes | FTR Vaski
47 | Statistics report on the number of searches |  |  |  |  | Duplicate! |  | check against original list => examples |  | Duplicate with #26 | Statistics | Yes | List from Vaski

## Closed
No. | Issue (Roadblocks => Red No fullfillment stage => Yellow) | Date last status change | Road block? | Priority 1 = highest 100 = lowest | SI number | Ex Libris' Comments | To be delivered with | Stage of fulfillment | Current Status | Next Steps | Actor | Description/Notes | Topic | Must have b4 go live? | Origin
6 | 16384-252435:: (L3 Problem Report) [358FIN] : Primo's OAI-PMH harvester doesn't... [deal with resumptionToken properly] | 2011-06-01 | Yes |  | 16384-252435 | Fixed on May-4 | 3.1 | Verification | Hotfix delivered, needs to be tested | Verify fix | NDL | resumptionToken problem; Roadblock for OvP; duplicate with 32 | BO publishing | Yes | SI list
17 | 2.3.2 A user should be able to authenticate himself using a library card issued by a Finnish library | 2011-06-01 | Yes |  |  | This issue is related to OvP. Moshe put the fix re. patron ID on NDL's servers - to be tested by NDL so that they can continue with OvP development for Axiell. | 3.1 | Verification | Allegedly solved but must be rolled out to NDL to verify function and continue OvP API setup for Axiell | currently tested by NDL | NDL | Issues with relaying patron id to OvP | OVP API | Yes | FTR Vaski

## original_merge_list
As of 5th May 2011
Descriptor | Comments | Vaski must have
16384-255080:: (L3 Problem Report) [358FIN] : Wrong links in emails sent from P |  | Maybe
16384-242192:: (L3 Problem Report) [358FIN] : eShelf and record folder notes do |  | Maybe
16384-239903:: (L3 Problem Report) [358FIN] : Stopping a pipe pending terminati | ExL w4i when another pipe is going to be started | Maybe
16384-255076:: (L3 Problem Report) [358FIN] : Security Issue: Emailing records |  | Yes
16384-254310:: (L3 Problem Report) [358FIN] : Primo does not sanitize email sub |  | Yes
16384-252435:: (L3 Problem Report) [358FIN] : Primo's OAI-PMH harvester doesn't |  | Yes
16384-247302:: (L3 Problem Report) [358FIN] : Primo should not suspect unsuppor | checking for 3.1.1 | Yes
16384-244695:: (L3 Problem Report) [358FIN] : Punctuation in brief results: (P |  | Yes
16384-242189:HIGH: (L3 Problem Report) [358FIN] : Security issue: Any user can | F&TR 5.10 maybe 3.1 | Yes
16384-241641:HIGH: (L3 Problem Report) [358FIN] : Security issue: Back Office / | 3.1 | Yes
16384-240952:: (L3 Problem Report) [358FIN] : Unable to terminate harvesting pi | it happens because of threads that are not finished - will be fixed - Sonja is checking when | Yes
16384-237819:: (L3 Problem Report) [358FIN] : Primo creates excessively long RS | F&TR 3.14 3.1 | Yes
16384-237973:: (L3 Problem Report) [358FIN] : Match of ISBN-10 to ISBN-13: (Pr | 3.1 | Yes
162096:: (L3 Problem Report) [49EXL] : How to customize character normalization | F&TR 3.16 + 15.2 3.1 | Yes
162125:HIGH: (L3 Problem Report) [358FIN] : Component parts: (Primo) Product M | see Aalborg | Yes (custom solution done)
1.8 The end user must be able to use persistent links to references (the link can be bookmarked, saved or sent by e.g. e-mail). | At least scandinavian characters in a search term are lost when a bookmarked search is repeated and no existing Primo session is active (SSO process encoding issue?) | Yes
2.3.2 A user should be able to authenticate himself using a library card issued by a Finnish library | Issues with relaying patron id to OvP | Yes
3.14 The end-user must be able to create alerts that send information on new references matching the search criteria by e-mail or RSS feed | RSS Feed URLs too long | Yes
4.2.1 It should be possible prioritise organisation's own material in its view of the public interface. We value customisability of the relevance ranking system. |  | Yes
6.1 The end-user must be able to check and renew loans |  | Yes
6.2 The end-user must be able to check and pay fees such as hold fees, overdue fees and other service fees (online payment etc.) |  | Yes (apart from paying fines)
6.3.1 The end-user must be able to reserve materials |  | Yes
6.3.4 The end-user must be able to do interlibrary loans and material requests |  | Maybe
6.3.7 The end-user must be able to check the availability of an item (for example holdings information) |  | Yes
9.2.1 Possibility to limit user session statistics reports based on user-groups, organisation and date interval. |  | Yes
9.8 The system should record statistics separately per access method (web interface, API etc.) and provide the possibility to distinguish between the methods in statistics reports. | E.g. the component parts implementation that uses X-Services must not skew the web interface usage statistics | Yes
10.13 Persistent URLs to all functions |  | Maybe
10.19 No limitation to session duration as long as the user has the service open in the browser (e.g. provide a possibility to use a JavaScript keep-alive callback to keep the session alive) | Local javascript? What url to use to keep the session alive? | Yes
10.23 Item availability status via batch load for facets and display of real time updated status per user affiliation (institution, IP address) |  | Yes
10.24.1 Possibility to display item availability by items' institutions and location on the search results list without having to move to a different per-record display |  | Yes
11.2 External authentication methods and extensions (OpenID, custom authentication hooks, e.g. library card number + PIN code from a local library, Finnish VETUMA identification and payment system) |  | Yes
12.1 Harvest records into the indexes using OAI-PMH protocol | resumptionToken problem, fix pending testing | Yes
12.9 Facets customisable per view (which ones are displayed, order of display) |  | Maybe
12.10 Relevance ranking | Need to be tested with real data | Yes
13.6 Retrieve and modify patron information, loans, holds and payments using SOAP or REST |  | Yes
15.2 Support Unicode (UTF-8) in all functions and provide conversions to/from other character sets e.g. ISO-8859-15 |  | Yes
15.3 Holds, loan renewals and item availability from library systems using APIs such as the ones specified by DLF's ILS-DI task group |  | Yes
18.3 24 / 7 continuous availability |  | Yes
Lightweight authentication (e.g. OpenID) | Priority needs to be checked with Turku | Maybe
Displaying of fees (amount and reason) |  | Yes
Displaying of patron's contact information (name, address, email, phone number) |  | Yes
Displaying of patron's active notification methods for request arrival notifications, overdue letters and due date notifications (email, SMS, letter) |  | Yes
Displaying of patron's loans (name of work, due date, number of renewals) |  | Yes
Renewal of loans |  | Yes
Requests, including requesting of on-shelf material |  | Yes
Performance of services | Needs to be adequate | Yes
Statistics report on the number of searches |  | Yes
Statistics report on the number of sessions |  | Yes